## Worksheet
Sprint Ticket ID | Type | Sprint Ticket/Requirement | Dev Status | Sprint # | Release Date | QA Resource
10414 | Bug | Student Virtual Classes list should be sorted latest first. | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Reopen
10418 | Bug | Login fails sometimes in the first attempt, then works fine in the second attempt. Check description | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
12512 | Bug | On the response screen , in a certain scenario, the user lands on the below shown screen without a back button appearing on the scree, The user has to relaunch the application to resume working on it. | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
13664 | Task | when an user searched for an entry in the concerns module, and its not in the list, some text should appear informing the user that no such entry exists in the system | Completed | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
13691 | Bug | There is no validation message for " no. of students" fields on the assign assignment/ study material screen. | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
13771 | Bug | The sorting for assignment should have the newest entry at top | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Active
15505 | Task | Provide ID Card download functionality in ID card screen. | Completed | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
15531 | Bug | Web App Issue : Evaluation delete issue | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Shahzeeb
15669 | Bug | Issue while selecting student for online class | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
15670 | Bug | Zoom meeting box accepting invalid URLs | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Reopen
15671 | Bug | User is able to create the online class for past time. | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
15676 | Bug | No save button on edit virtual class screen | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
17410 | Task | Create PTM screen as seen in the web-app. | Completed | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
17952 | Task | Implement pagination in News/Notice/Circular list screen. Check description | Completed | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Reopen
18398 | Task | Students should be able to see health screen as seen in the web-app. Check description | Completed | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Shahzeeb
18493 | Bug | Instructor is not able to download attachments in assignment evaluation screen. Check description | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
18507 | Bug | Cancel date not shown correct in assignment detail screen. Check screenshot | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Halted(Moved to backlog)
18508 | Bug | Date assigned not shown correct in assignments list screen. Check screenshot | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Halted(Moved to backlog)
18672 | Bug | Employee timetable issue | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
18681 | Bug | Issue with parent login having no student linked. | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
18683 | Bug | Online Classes> Username name appears as null on comment screen | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Halted(Moved to backlog)
18768 | Bug | Student/Teacher is not unable to receive any news/notice/circular | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
18861 | Task | News/Notice/Circular list screen should show pinned items. Check description. | Completed | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
18921 | Task | Show custom labels in all screens wherever available. Check description. | Completed | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Shahzeeb
19022 | Task | Improvements to the user interface and refactoring of the code on the live location of the assigned transport vehicle. Check description. | Completed | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Hold
19100 | Task | Reopen 18378 | Completed | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
19108 | Bug | User is unable to upload .bmp file and view supporting document. | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Closed
19128 | Bug | Notification history > Message not appearing | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Shahzeeb
17185 | Bug | Data on downloaded ID card is overlapping and data is also missing | Resolved | Educian Mobile 2.0\Sprint-54 | 17-11-2022 | Fehad | Reopen